## Campus-Sink - GanttChart_1
[6 empty] | April 2025 | [6 empty] | May 2025 | [30 empty] | June 2025 | [29 empty] | July 2025 | [30 empty] | August 2025 | [30 empty] | September 2025 | [29 empty] | October 2025
Workstream | Task | Team | Duration | Start Date | End Date | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Planning
| Conduct project kickoff meeting to align goals and roles. | Full Team | 1 | 2025-04-24 | 2025-04-24
Requirement Analysis
| Gather detailed requirements and user stories for the dashboard. | Designers | 5 | 2025-04-25 | 2025-05-01
Design
| Create wireframes and UI designs in Figma. | Designers | 7 | 2025-05-02 | 2025-05-12
| Review after changes any need and get approval on UI designs from all team members. | Designers | 18 | 2025-05-13 | 2025-05-31
Development
| Set up project repository and environment for frontend and backend. | Developers | 1 | 2025-06-07 | 2025-06-07
| Develop the backend using Node.js and Express for API integration. | Developers | 5 | 2025-06-08 | 2025-06-12
| Set up MongoDB database for data storage and management. | Developers | 3 | 2025-06-13 | 2025-06-15
| Develop the frontend using React.js for the dashboard UI. | Developers | 5 | 2025-06-13 | 2025-06-17
| Implement API calls for backend integration in the frontend. | Developers | 3 | 2025-06-18 | 2025-06-20
Testing
| Conduct unit testing for backend API endpoints. | QA | 2 | 2025-06-14 | 2025-06-15
| Conduct unit testing for frontend components. | QA | 2 | 2025-06-16 | 2025-06-17
| Perform integration testing for frontend and backend functionalities. | QA | 2 | 2025-06-18 | 2025-06-19
| Conduct user acceptance testing with selected stakeholders. | QA | 1 | 2025-06-20 | 2025-06-20
Deployment
| Deploy the application on AWS,Vercel/Render/Netlify. | Developers | 1 | 2025-06-20 | 2025-06-20
Refinement
| Gather feedback and make necessary iterations on UI and functionalities. | Designers | 1 | 2025-06-20 | 2025-06-20
| Fixing the bugs |  | 1 | 2025-06-20 | 2025-06-20
Documentation
| Prepare final documentation and user guides for the platform. | Developers | 1 | 2025-06-20 | 2025-06-20
Plan
VS
Available Team:- |  |  |  | Actual
Designers:- | Shravani,Diksha
Developers:- | Dhiraj,Shivshankar,Shravani,Diksha
QA:- | Diksha,Shravani
[6 empty] | April 2025 | [6 empty] | May 2025 | [30 empty] | June 2025
Workstream | Task | Team | Duration | Actual Start Date | Actual End Date | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Planning | bar: June 2025 21
| Conduct project kickoff meeting to align goals and roles. | Full Team | 3 | 2025-04-25 | 2025-04-27 | bar: April 2025 25 to April 2025 27; June 2025 21
Requirement Analysis | bar: June 2025 21
| Gather detailed requirements and user stories for the dashboard. | Designers | 35 | 2025-04-26 | 2025-05-30 | bar: April 2025 26 to April 2025 30; June 2025 21
Design | bar: June 2025 21
| Create wireframes and UI designs in Figma. | Designers | 7 | 2025-05-04 | 2025-05-10 | bar: May 2025 4 to May 2025 10; June 2025 21
| Review after changes any need and get approval on UI designs from all team members. | Designers | 18 | 2025-05-14 | 2025-05-31 | bar: May 2025 14 to May 2025 31; June 2025 21
Development | bar: June 2025 21
| Set up project repository and environment for frontend and backend. | Developers | 2 | 2025-06-08 | 2025-06-09 | bar: June 2025 8 to June 2025 9; June 2025 21
| Develop the backend using Node.js and Express for API integration. | Developers | 5 | 2025-06-10 | 2025-06-14 | bar: June 2025 6; June 2025 10 to June 2025 14; June 2025 20 to June 2025 21; June 2025 27
| Set up MongoDB database for data storage and management. | Developers | 5 | 2025-06-13 | 2025-06-17 | bar: June 2025 13 to June 2025 17; June 2025 21
| Develop the frontend using React.js for the dashboard UI. | Developers | 7 | 2025-06-14 | 2025-06-20 | bar: June 2025 14 to June 2025 21
| Implement API calls for backend integration in the frontend. | Developers | 4 | 2025-06-18 | 2025-06-21 | bar: June 2025 18 to June 2025 21
| Enhancing the UI | Developers | 5 | 22-06-2025 | 2025-06-26 | bar: June 2025 22 to June 2025 26
| Implementing calendar functionality | Developers | 5 | 2025-06-27 | 2025-07-01 | bar: June 2025 27 to June 2025 30
Testing | bar: June 2025 21
| Conduct unit testing for backend API endpoints. | QA | 3 | 2025-07-17 | 2025-07-19 | bar: June 2025 21
| Conduct unit testing for frontend components. | QA | 8 | 2025-07-19 | 2025-07-26
| Perform integration testing for frontend and backend functionalities. | QA | 4 | 2025-07-26 | 2025-07-29
| Conduct user acceptance testing with selected stakeholders. | QA | 5 | 2025-07-29 | 2025-08-02
Deployment | bar: June 2025 21
| Deploy the application on AWS,Vercel/Render/Netlify. | Developers | 13 | 2025-07-21 | 2025-08-02
Refinement | bar: June 2025 21
| Gather feedback and make necessary iterations on UI and functionalities. | Designers | 3 | 2025-08-03 | 2025-08-05
| Fixing the bugs |  | 3 | 2025-08-06 | 2025-08-08
Documentation | bar: June 2025 21
| Prepare final documentation and user guides for the platform. | Developers | 4 | 2025-08-08 | 2025-08-11